## Main
No. | Product Deliverables | Task | Afifah | Bazilah | Hafiy | Omar | Rahimah | Status
1 | Planning | Design Document
|  | - Story Summary | [5 empty] | **
|  | - Game Discription | [5 empty] | **
|  | - Gameplay | [5 empty] | **
|  | - Gameflow Diagrams | [5 empty] | ** | Status |  | Not started
|  | Concept Art | [7 empty] | * | Currently Doing
|  | - Sketches of each characters |  |  | o |  |  | * |  | ** | Finished but probably will add on later
|  | - Sketches of the game world | o | [6 empty] | *** | DONE !
Map Design
|  | - Cave | o |  |  |  |  | *
- Ocean
- Ground
- Forest
- Snowy Place
- Sky City
- Space
2 | Story | Script and Dialogue (Story)
|  | - Prologue | o
3 | Art and Prefabs | 3D Environment Asset
|  | - One very tall building |  |  |  | o
2D Character Asset
- Main Character Sprite
|  | - Cat | o |  | o |  |  | **
- Dog
- Monkey
- Types of Enemies
|  | - Bat |  |  | o |  |  | **
|  | - Snake |  |  | o |  |  | **
|  | - Caveman | [5 empty] | *
|  | - Spider |  |  | o |  |  | **
|  | - Piranha |  |  | o
|  | - Shark |  |  | o
|  | - Octopus |  |  | o
|  | - Fishman |  |  | o
- Ghost
- Vampire
- Skeleton
- Mutant
- Boar
- Dinosour
- Poacher
- Tree Snake (More greener?)
- Vultures
- Sky Pirates
- War Plane
- Dragon
- Alien
- Alien animal
- Scary Alien
Normal Coins
Special Coins
Power Ups
- Makes character invicible and enter super fast mode for 5 seconds
4 | Animations | Idle |  | o |  |  | o | *
|  | Walking |  | o |  |  | o | *
|  | Running |  | o |  |  | o | *
|  | Jumping |  | o |  |  | o
|  | Shooting |  | o |  |  | o
|  | Attacking |  | o |  |  | o
5 | UI | Main Menu
|  | - Start |  |  |  |  | o
- Score
- Option
- Change Character
Heath
Score (coin collected + total height achieved)
Highscore
Change Character Screen
Pause Screen
Option Screen
- Disable Audio (BG Music, SFX)
- Game Informations
6 | Audio | Main BGM | o
Jumping SFX
Landing SFX
Walking SFX
Dying SFX
|  | Shooting SFX | o
Enemy Dying SFX
7 | Scripting | Interaction Matrices
|  | Control Movement | o |  | o |  |  | *
|  | Camera Controller | o |  | o |  |  | *
Game Over Trigger
Health Depleting
Automatic Save State
Collecting Item
Different character, different ability
8 | Final | Testing
Upload on Google Play

## Prefabs Checklist
No | Name | Animation | [9 empty] | Audio
|  | Idle | Walking | Running | Flying | Swimming | Jumping | Shooting | Attacking | Hit | Dying | Footsteps | Attack | Hit | Died
1 | Cat
2 | Dog
3 | Monkey
4 | Bat
5 | Snake
6 | Caveman
7 | Spider | [14 empty] | Doesn't have to
8 | Piranha | [14 empty] | For Hit SFX, every prefabs is the same
9 | Shark
10 | Octopus
11 | Fishman
12 | Ghost
13 | Vampire
14 | Skeleton
15 | Mutant
16 | Boar
17 | Dinosour
18 | Poacher
19 | Tree Snake
20 | Vultures
21 | Sky Pirates
22 | War Plane
23 | Dragon
24 | Alien
25 | Alien animal
26 | Scary Alien